## Sheet1
[Company Logo] |  | Wena's Online Ordering Platform Test Script
Project Name |  | Wena's Online Ordering Platform
Project Manager |  | Muros, Adrian A.
Business Analyst
Testing Start Date
Testing End Date
Name of Tester: |  | Karl Evlan Robasto, Marc Niel Bides, Darelle Yuri, Soriano
Phase / Release Number: |  | Version 1.0
ID# | Description | Preconditions / Data | Steps To Execute | Expected Behavior | Actual Behavior | Passed | Failed | Retest Date | Defect/Comments
CUSTOMER PORTAL
1 | Home Page – Load | User has access to the app URL. | 1) Open browser. 2) Go to http://localhost:5173. 3) Wait for page to load. | Home page loads with store name, featured products, categories, navigation bar, and public stats (total products, delivered orders, total customers).
2 | Browse by Category | User is on the home page. Categories exist. | 1) Click on a category (e.g., 'Tools'). 2) Observe products. | Products page shows only products from the selected category.
3 | View All Products | Products exist in the database. | 1) Click 'Products' in the nav bar. 2) Observe product listing. | Products displayed in a paginated grid with name, price, and image.
4 | Search Products | User is on Products page. | 1) Type 'Hammer' in the search bar. 2) Observe results. | Only products matching 'Hammer' are shown. Search is debounced.
5 | Filter by Category | User is on the Products page. | 1) Select a category filter (e.g., 'Electrical'). 2) Observe results. | Only products in the selected category are shown.
6 | Product Detail Page | User is on the Products page. | 1) Click on a product card. 2) Observe the detail page. | Detail page shows name, description, price, SKU, stock, images, variants, and bulk pricing.
7 | Select Product Variant | Product with variants exists (e.g., sizes). | 1) Go to a product with variants. 2) Select a variant (e.g., 'Large'). | Price and stock update to reflect the selected variant.
8 | View Bulk Pricing | Product with bulk pricing tiers exists. | 1) Go to product detail. 2) View bulk pricing section. | Pricing tiers shown (e.g., '10+ units: ₱300 each').
SHOPPING CART
9 | Add to Cart | User is on a product detail page. | 1) Set quantity to 2. 2) Click 'Add to Cart'. | Success notification shown. Cart icon updates with item count.
10 | View Cart | User has items in the cart. | 1) Click the cart icon in the nav bar. | Cart page shows items with name, price, quantity, and total.
11 | Update Cart Quantity | User is on the Cart page with at least one item. | 1) Change quantity from 2 to 5. 2) Observe totals. | Subtotal and order total recalculate. Quantity clamped to available stock.
12 | Remove Cart Item | User has items in the cart. | 1) Click 'Remove' on an item. 2) Confirm if prompted. | Item removed. Total recalculates. Empty cart message if no items left.
13 | Empty Cart – No Checkout | Cart is empty. | 1) Go to Cart page. 2) Try to proceed to checkout. | Checkout button is disabled or shows 'cart is empty' message.
14 | Add Variant to Cart | Product with variants exists. | 1) Go to product detail. 2) Select a variant. 3) Click 'Add to Cart'. | Variant added as separate cart item with correct variant name and price.
15 | Cart Item Selection | User has multiple items in the cart. | 1) Uncheck one item. 2) Observe totals. | Only selected (checked) items are included in subtotal. Unselected items remain in cart but are excluded from checkout.
16 | Cart Stock Validation | User has items in cart. Stock was reduced externally. | 1) Open cart page. 2) Observe stock refresh. | Cart validates stock from server. Quantities clamped to available stock. Warning shown if stock changed.
17 | Cart Persistence Across Sessions | User has items in the cart. | 1) Close browser tab. 2) Reopen app. | Cart items persist from localStorage.
18 | Cart Isolation Per Customer | Two customer accounts exist. Customer A has items in cart. | 1) Log out as Customer A. 2) Log in as Customer B. | Customer B sees their own cart (empty or separate). Customer A's cart is not visible.
CHECKOUT & ORDERS
19 | Place Order (Guest) | Cart has items. User is NOT logged in. | 1) Click 'Proceed to Checkout'. 2) Fill: Name, Phone (09171234567), Address, Barangay. 3) Click 'Place Order'. | Order placed. Redirected to confirmation page with order number.
20 | Place Order (Logged-in Customer) | Cart has items. Customer is logged in. | 1) Click 'Proceed to Checkout'. 2) Verify pre-filled fields. 3) Click 'Place Order'. | Order placed with customerId linked. Redirected to confirmation page.
21 | Checkout – Use Saved Address | Customer is logged in with saved addresses. | 1) Click 'Proceed to Checkout'. 2) Select a saved address from dropdown. 3) Click 'Place Order'. | Address fields auto-fill from saved address. Order placed successfully.
22 | Checkout – Phone Validation | User is on checkout page. | 1) Enter invalid phone (e.g., '12345'). 2) Click 'Place Order'. | Validation error shown. Order NOT placed.
23 | Checkout – Required Fields | User is on checkout page. | 1) Leave Name and Address blank. 2) Click 'Place Order'. | Validation errors for all required fields. Order NOT placed.
24 | Order with Variant | Product with variants exists. | 1) Select variant 'Red – 1 Liter'. 2) Add to cart, checkout, place order. | Order shows correct variant name and variant-specific price.
25 | Order with Bulk Pricing | Product has bulk pricing: 10+ = ₱300 each (normal ₱350). | 1) Add 15 units to cart. 2) Checkout and place order. | Bulk price ₱300 applied. Total = ₱4,500.
26 | Order with Multiple Items | Multiple products exist. | 1) Add Product A (qty 2), Product B (qty 1), Product C (qty 5). 2) Checkout and place order. | Order contains all 3 items with correct quantities and totals.
27 | Cart Validation Before Checkout | Cart has items. One product is now out of stock. | 1) Click 'Proceed to Checkout'. 2) Observe validation. | Validation shows which items are unavailable or have insufficient stock. Checkout blocked until resolved.
28 | Track Order – Valid Number | Order HW-20260212-0001 exists. | 1) Click 'Track Order'. 2) Enter order number. 3) Click 'Track'. | Order details shown: status, items, total, customer info, status history.
29 | Track Order – Invalid Number | User is on Track Order page. | 1) Enter 'INVALID-123'. 2) Click 'Track'. | Error message: order not found.
30 | Track Order – Rate Limiting | User is on Track Order page. | 1) Rapidly submit 20+ tracking requests. | Rate limit error shown after threshold. User must wait before retrying.
CUSTOMER ACCOUNTS
31 | Customer Registration | No account with test email exists. | 1) Click 'Register'. 2) Name: 'Juan Dela Cruz', Email: 'juan@example.com', Password: 'Securepass123!'. 3) Click 'Register'. | Account created. User logged in and redirected.
32 | Registration – Duplicate Email | Account with 'juan@example.com' already exists. | 1) Try registering with same email. 2) Click 'Register'. | Error: email already registered.
33 | Registration – Weak Password | User is on registration page. | 1) Enter password: 'abc'. 2) Click 'Register'. | Validation error: password must be 8+ chars with uppercase, lowercase, number, and special character.
34 | Customer Login | Account exists: juan@example.com / Securepass123!. | 1) Click 'Login'. 2) Enter email and password. 3) Click 'Login'. | User logged in. Nav shows user name and account options.
35 | Login – Invalid Credentials | User is on Login page. | 1) Enter email: 'juan@example.com'. 2) Enter wrong password. 3) Click 'Login'. | Error: invalid credentials. User NOT logged in.
36 | Customer Logout | Customer is logged in. | 1) Click user menu. 2) Click 'Logout'. | Customer logged out. Redirected to home page. Account options hidden.
37 | View Profile | Customer is logged in. | 1) Navigate to 'Account' page. | Profile shows name, email, phone, and counts (orders, addresses, wishlist items).
38 | Update Profile | Customer is logged in. | 1) Change name to 'Juan D. Cruz'. 2) Click 'Save'. | Profile updated. Changes persist on reload.
39 | Change Password | Customer is logged in. | 1) Enter current password. 2) Enter new password (meets strength requirements). 3) Click 'Change Password'. | Password updated. Can log in with new password.
40 | View Order History | Customer is logged in with past orders. | 1) Navigate to 'Order History'. | Paginated list of past orders with order number, date, status, total.
41 | View Order Detail (Customer) | Customer is logged in with past orders. | 1) Click on an order in Order History. | Order detail shows items, quantities, prices, total, and status history. Only shows own orders.
42 | Cancel Own Order | Customer is logged in. Has a 'pending' order. | 1) Go to Order History. 2) Click on the pending order. 3) Click 'Cancel Order'. 4) Confirm. | Order status changes to 'cancelled'. Stock restored. Order shows updated status.
43 | Add Saved Address | Customer is logged in. | 1) Go to 'Saved Addresses'. 2) Click 'Add'. 3) Fill label, address, barangay. 4) Click 'Save'. | Address saved. If first address, automatically set as default.
44 | Edit Saved Address | Customer has a saved address. | 1) Click 'Edit' on an address. 2) Change address fields. 3) Click 'Save'. | Address updated. Changes persist.
45 | Delete Saved Address | Customer has a saved address. | 1) Click 'Delete' on an address. 2) Confirm. | Address removed from the list. If default was deleted, another address auto-assigned as default.
46 | Set Default Address | Customer has multiple saved addresses. | 1) Click 'Set as Default' on a non-default address. | Selected address marked as default. Previous default unmarked.
47 | Add to Wishlist | Customer is logged in. | 1) Go to a product page. 2) Click 'Add to Wishlist'. | Product added. Heart icon becomes filled. Wishlist count updates.
48 | View Wishlist | Customer has wishlist items. | 1) Navigate to 'Wishlist'. | Wishlist items shown with name, price, image. Add to cart option available.
49 | Remove from Wishlist | Customer has wishlist items. | 1) Click 'Remove' on a wishlist item. | Item removed from wishlist. Heart icon unfills on product page.
50 | Add to Cart from Wishlist | Customer has items in wishlist. | 1) Go to 'Wishlist'. 2) Click 'Add to Cart' on an item. | Item added to cart from wishlist page.
PASSWORD RESET
51 | Forgot Password – Request Reset | Customer account exists with 'juan@example.com'. | 1) Go to Login page. 2) Click 'Forgot Password'. 3) Enter email: 'juan@example.com'. 4) Click 'Submit'. | Success message shown (regardless of whether email exists, to prevent enumeration). Reset email sent.
52 | Forgot Password – Non-existent Email | No account with 'unknown@example.com' exists. | 1) Go to Forgot Password page. 2) Enter email: 'unknown@example.com'. 3) Click 'Submit'. | Same success message shown (no email enumeration). No email sent.
53 | Reset Password – Valid Token | Password reset email received with valid token. | 1) Click reset link from email. 2) Enter new password meeting strength requirements. 3) Click 'Reset Password'. | Password reset successfully. Can log in with new password. Token invalidated.
54 | Reset Password – Expired/Invalid Token | Token is expired or invalid. | 1) Navigate to reset page with invalid/expired token. 2) Try to reset password. | Error: token is invalid or expired. User prompted to request new reset.
55 | Reset Password – Weak Password | Valid reset token exists. | 1) Click reset link. 2) Enter weak password (e.g., '123'). 3) Click 'Reset Password'. | Validation error: password does not meet strength requirements.
ADMIN – LOGIN & DASHBOARD
56 | Admin Login | Admin account: admin / admin123. | 1) Go to /admin/login. 2) Enter username and password. 3) Click 'Login'. | Admin logged in. Redirected to Dashboard.
57 | Admin Login – Invalid | User is on admin login page. | 1) Enter wrong password. 2) Click 'Login'. | Error: invalid credentials.
58 | Admin – Protected Routes | Admin is NOT logged in. | 1) Go to /admin directly. | Redirected to admin login page.
59 | Dashboard – Statistics | Admin is logged in. Orders exist. | 1) View the Dashboard page. | Shows total orders, today's orders, pending orders, total products, today's revenue, and 5 recent orders.
60 | Admin Logout | Admin is logged in. | 1) Click 'Logout'. | Admin logged out. Redirected to login page.
61 | Admin – Change Own Password | Admin is logged in. | 1) Navigate to change password. 2) Enter current password. 3) Enter new password. 4) Click 'Change Password'. | Password updated. Can log in with new password.
ADMIN – ORDER MANAGEMENT
62 | View All Orders | Admin is logged in. Orders exist. | 1) Click 'Orders' in sidebar. | Orders listed with order number, customer, status, total, date.
63 | Filter Orders by Status | Admin is on Orders page. Orders with various statuses exist. | 1) Select status filter (e.g., 'Pending'). 2) Observe results. | Only orders with selected status are shown.
64 | Search Orders | Admin is on Orders page. | 1) Type order number, customer name, or phone in search. 2) Observe results. | Orders matching the search query are shown.
65 | Filter Orders by Date Range | Admin is on Orders page. | 1) Select start and end date. 2) Observe results. | Only orders within the date range are shown.
66 | View Order Details | Admin is on Orders page. | 1) Click on an order. | Full order details: customer info, items, total, status history, SMS logs.
67 | Accept Order | A 'pending' order exists. | 1) Open a pending order. 2) Click 'Accept'. | Status changes to 'accepted'. History updated.
68 | Reject Order | A 'pending' order exists. | 1) Open a pending order. 2) Click 'Reject'. | Status changes to 'rejected'. History updated. Stock restored.
69 | Full Status Workflow | An 'accepted' order exists. | 1) Change to 'Preparing'. 2) Then 'Out for Delivery'. 3) Then 'Delivered'. 4) Then 'Completed'. | Each status transition succeeds. History logs each change with timestamp and user.
70 | Cancel Order | A pending or accepted order exists. | 1) Open the order. 2) Click 'Cancel'. 3) Confirm. | Status changes to 'cancelled'. Stock restored.
ADMIN – PRODUCT MANAGEMENT
71 | View Products List | Admin is logged in. | 1) Click 'Products' in sidebar. | Products listed with name, SKU, category, price, stock, status.
72 | Create Product | Admin is logged in. A category exists. | 1) Click 'Add Product'. 2) Fill: Name, SKU, Price, Category, Stock. 3) Click 'Save'. | Product created. Appears in product list.
73 | Edit Product | A product exists. | 1) Click 'Edit' on a product. 2) Change the price. 3) Click 'Save'. | Product updated. New price reflected.
74 | Delete Product | A product exists with no pending orders. | 1) Click 'Delete' on a product. 2) Confirm. | Product soft-deleted. Hidden from storefront.
75 | Delete Product – Active Orders Block | A product has active (pending/accepted/preparing) orders. | 1) Click 'Delete' on the product. 2) Confirm. | Error: cannot delete product with active orders.
76 | Toggle Availability | A product is currently available. | 1) Click the availability toggle. | Product availability toggled off. Not purchasable on storefront.
77 | Update Product Stock | A product exists. | 1) Edit product. 2) Change stock quantity and low stock threshold. 3) Save. | Stock updated. Low stock threshold saved.
78 | View Low Stock Products | Products below their low stock threshold exist. | 1) Navigate to low stock inventory view. | Products with stock below threshold are listed with current stock and threshold.
79 | Add Product Variant | A product exists. | 1) Edit product. 2) Add variant: Name, SKU, Price, Stock. 3) Save. | Variant created. Product's hasVariants flag set. Customers can select it.
80 | Edit Product Variant | A product variant exists. | 1) Edit product. 2) Modify variant name/price/stock. 3) Save. | Variant updated. Changes reflected on product detail page.
81 | Delete Product Variant | A product variant exists. | 1) Edit product. 2) Click 'Delete' on a variant. 3) Confirm. | Variant soft-deleted. No longer selectable on storefront.
82 | Update Variant Stock | A product variant exists. | 1) Edit product. 2) Update variant stock quantity. 3) Save. | Variant stock updated independently from main product stock.
83 | Add Bulk Pricing Tier | A product exists. | 1) Edit product. 2) Add tier: Min Qty 10, Price 300. 3) Save. | Bulk pricing tier saved. Product's hasBulkPricing flag set. Shown on product page.
84 | Edit Bulk Pricing Tier | A bulk pricing tier exists. | 1) Edit product. 2) Modify tier values. 3) Save. | Tier updated. New pricing reflected on product page.
85 | Delete Bulk Pricing Tier | A bulk pricing tier exists. It is the only tier. | 1) Edit product. 2) Delete the tier. 3) Confirm. | Tier deleted. Product's hasBulkPricing flag auto-disabled.
86 | Upload Product Image | A product exists. | 1) Edit product. 2) Upload a JPG/PNG image. 3) Save. | Image uploaded. Shown on product page. First image auto-set as primary.
87 | Upload Multiple Product Images | A product exists. | 1) Edit product. 2) Upload multiple images (up to 10). 3) Save. | All images uploaded. Gallery shown on product detail page.
88 | Set Primary Image | A product has multiple images. | 1) Edit product. 2) Click 'Set as Primary' on a non-primary image. | Selected image set as primary. Product thumbnail updated.
89 | Reorder Product Images | A product has multiple images. | 1) Edit product. 2) Drag/reorder images. 3) Save. | Image sort order updated. Gallery reflects new order.
90 | Delete Product Image | A product has multiple images. | 1) Edit product. 2) Click 'Delete' on an image. 3) Confirm. | Image removed from gallery and disk. If primary was deleted, next image auto-assigned as primary.
91 | Upload Invalid File Type | A product exists. | 1) Edit product. 2) Try uploading a .gif or .pdf file. | Error: only JPEG, PNG, and WebP formats accepted.
92 | Upload Oversized Image | A product exists. | 1) Edit product. 2) Try uploading an image >5MB. | Error: file size exceeds 5MB limit.
ADMIN – CATEGORY MANAGEMENT
93 | View Categories | Admin is logged in. | 1) Click 'Categories' in sidebar. | Categories listed with name, description, product count.
94 | Create Category | Admin is logged in. | 1) Click 'Add Category'. 2) Enter name and description. 3) Save. | Category created. Available in product dropdowns.
95 | Edit Category | A category exists. | 1) Click 'Edit'. 2) Change description. 3) Save. | Category updated.
96 | Delete Category | A category with no products exists. | 1) Click 'Delete'. 2) Confirm. | Category deleted. No longer in dropdowns.
97 | Delete Category – Has Products | A category has active products assigned. | 1) Click 'Delete'. 2) Confirm. | Error: cannot delete category with active products.
ADMIN – REPORTS & STAFF
98 | View Sales Report | Admin is logged in. Sales data exists. | 1) Click 'Reports' in sidebar. 2) View Sales tab. | Sales report shows total revenue, order counts, completed/cancelled stats, average order value, daily breakdown chart, and growth comparison.
99 | View Product Report | Admin is logged in. Order data exists. | 1) Click 'Reports'. 2) View Product tab. | Product report shows top 10 products by revenue and category statistics (product count, total sold, revenue).
100 | Export Sales Report as CSV | Admin is logged in. Orders exist. | 1) Click 'Reports'. 2) Click 'Export CSV'. | CSV file downloaded with full order data including items.
101 | Create Staff User | Admin is logged in with 'admin' role. | 1) Go to user management. 2) Add user: username, name, password, role 'staff'. 3) Save. | Staff account created. Can log in to admin panel.
102 | Edit Staff User | Staff user exists. | 1) Go to user management. 2) Click 'Edit' on staff user. 3) Change name or role. 4) Save. | User updated. Changes reflected.
103 | Deactivate Staff User | Staff user exists. | 1) Go to user management. 2) Click 'Deactivate' on a staff user. 3) Confirm. | User deactivated (soft delete). Cannot log in. Preserved in audit trails.
104 | Protect Last Admin | Only one admin user exists. | 1) Try to delete or demote the last admin user. | Error: cannot delete or demote the last admin. Operation blocked.
105 | Staff Login & Limited Access | Staff account exists. | 1) Log in as staff. 2) Try to access user management. | Staff can access orders, products, categories. User management restricted to admin role.
SMS NOTIFICATIONS
106 | SMS – Order Confirmation | SMS_ENABLED=true. SMS provider configured. | 1) Place a new order with a valid phone. 2) Check SMS logs. | SMS sent to customer with order number and summary.
107 | SMS – Order Accepted | SMS enabled. Pending order exists. | 1) Admin accepts order. 2) Check SMS logs. | SMS sent notifying customer order was accepted.
108 | SMS – Order Rejected | SMS enabled. Pending order exists. | 1) Admin rejects order. 2) Check SMS logs. | SMS sent notifying customer order was rejected.
109 | SMS – Out for Delivery | SMS enabled. Order in 'preparing' status. | 1) Admin changes status to 'Out for Delivery'. 2) Check SMS logs. | SMS sent notifying customer order is on the way.
110 | SMS – Delivered | SMS enabled. Order in 'out_for_delivery' status. | 1) Admin changes status to 'Delivered'. 2) Check SMS logs. | SMS sent confirming delivery.
111 | SMS – Admin New Order Alert | SMS enabled. Admin notification configured. | 1) Customer places a new order. 2) Check admin SMS logs. | SMS alert sent to admin about new order.
112 | SMS – Disabled Mode | SMS_ENABLED=false in .env. | 1) Place a new order. 2) Check SMS logs. | No SMS sent. Order placed without errors.
113 | SMS – Phone Format Handling | SMS enabled. | 1) Place orders with: '09171234567', '+639171234567', '9171234567'. | All phone formats accepted and normalized. SMS sent for each.
114 | SMS – Provider Fallback | Primary SMS provider (Semaphore) is down. Fallback provider configured. | 1) Place an order. 2) Check SMS logs. | SMS sent via fallback provider (Movider/Vonage). Retry logged.
115 | SMS – View SMS Logs in Order | Admin is viewing an order that triggered SMS. | 1) Open order detail in admin. 2) View SMS logs section. | SMS logs shown with phone, message, status (sent/failed/pending), timestamp.
UI / UX
116 | Responsive Layout | User has access to the app. | 1) Open app on desktop. 2) Resize to mobile width (< 768px). | Layout adjusts. Nav becomes hamburger menu. All features accessible.
117 | 404 Page | User has access to the app. | 1) Navigate to /nonexistent. | 404 page shown with link back to home.
118 | Loading States | User has access to the app. | 1) Navigate between pages. 2) Observe loading indicators. | Loading spinner or skeleton shown while content loads.
119 | Protected Customer Routes | User is NOT logged in as customer. | 1) Navigate to /account directly. | Redirected to login page. After login, redirected back to account.
120 | Error Boundary | App encounters a rendering error. | 1) Trigger a component error (e.g., corrupt data). | Error boundary catches the error. Friendly error message shown instead of blank page.
121 | Lazy Loading / Code Splitting | User has access to the app. | 1) Open browser DevTools Network tab. 2) Navigate between pages. | Pages load as separate chunks. Initial bundle size is optimized.
122 | Image Lazy Loading | Page has many product images. | 1) Open a product listing page. 2) Scroll down slowly. | Images load lazily as they enter the viewport. Placeholder shown before load.
SECURITY & INFRASTRUCTURE
123 | Rate Limiting – Auth Endpoints | User is on login page. | 1) Attempt 20+ rapid login requests with wrong credentials. | Rate limit error returned after threshold. User must wait before retrying.
124 | XSS Prevention | User is on checkout page. | 1) Enter '<script>alert(1)</script>' in the Name field. 2) Place order. | Input is sanitized. Script tags are encoded, not executed. Order saved safely.
125 | JWT Token Expiry | User is logged in. Token has expired. | 1) Wait for token to expire. 2) Try to access a protected route. | Automatically redirected to login page. Must re-authenticate.
126 | Health Check Endpoint | Server is running. | 1) Send GET request to /health. | Returns 200 OK with health status.